## Leevi Määttä
Ryhmä: | 13
Pvm | Tehtävä | Leevi Määttä
2025-11-04 | Käyttöliitymän suunnittelu | 2
2025-11-04 | Tietokannan suunnittelu | 2
2025-11-05 | Versionhallinan käyttöönotto | 2
2025-11-06 | Docker käyttöönotto | 3
2025-11-10 | Backendin aloitus | 4
2025-11-12 | Backendin user toiminnot | 3
2025-11-13 | Frontend kuvanhaku ja API yhteys | 4
2025-11-17 | Backend/frontend hakupalkki | 3
2025-11-17 | Käyttöliittymän tyylin teko | 2
2025-11-18 | Backend/frontend discover sivu | 6
2025-11-18 | Hakupalkin parantelu | 1
2025-11-19 | Hakupalkin parantelu | 1
2025-11-19 | Discover sivun parantelu | 2
2025-11-20 | Ryhmät sivun tekeminen | 3
2025-11-21 | Backend ryhmätoiminnot | 4
2025-12-22 | Ryhmä sivun tekeminen | 4
2025-12-25 | Ryhmien liittymispyyntöjen parantaminen | 2
2025-11-26 | Ryhmätoimintojen parantaminen | 4
2025-12-02 | Loputon scrollaus toiminnon tekeminen | 4
2025-12-02 | Bugien korjauksia | 2
2025-12-03 | Bugien korjauksia | 3
2025-12-07 | Sivun julkaisu railwayssa | 4
2025-12-08 | Sivun julkaisu railwayssa | 3
2025-12-08 | Yleisesti käyttöliittymän parantelua ja korjauksia | 4
2025-12-09 | Ryhmäsivun korjauksia | 2
2025-12-10 | Yleisesti käyttöliittymän parantelua ja korjauksia | 2
2025-12-15 | Backend testien teko | 6
2025-12-17 | Yleisesti käyttöliittymän parantelua ja korjauksia | 3
| Yhteensä: | 85

## Tomi Roumio
Ryhmä: | 9
Pvm | Tehtävä | Tomi Roumio
2025-11-10 | Merge of PR #4 into main (integration) | 1
2025-11-11 | Added CONTRIBUTING.md and refreshed README documentation for contribution guidelines | 1
2025-11-12 | Reorganized repository by moving frontend into client/, updated Docker/Vite/eslint configs and moved source files into the client folder | 3
2025-11-13 | Merged main into client-move branch (integration) | 0.25
2025-11-14 | Merged PR from leevi into main (integration) | 0.25
2025-11-15 | Minor README clarification note & Added debugging notes to DEBUG.md to help future troubleshooting | 0.25
2025-11-16 | Major TMDB backend integration: added controllers, helpers and routes for movies, TV | 4
2025-11-17 | Major TMDB backend integration: added search, genres and reviews to expose TMDB-backed API surfaces | 4
2025-11-18
2025-11-19 | Implemented full Movie Detail feature: frontend pages/components (MovieDetail, GetMoviesSeries, App integration), styles, and backend TMDB endpoints/helpers to serve required movie data | 6
2025-11-20 | Fixed bugs in TMDB controllers/helpers to correct movie and TV lookup behavior and returned data shape | 2
2025-11-21
2025-11-22 | README updates and clarifications | 1
2025-11-23 | README edits (project info, formatting) | 1
2025-11-24
2025-11-25 | Added favorite (❤️) and add-to-group (➕) UI controls and handlers across AddToGroupModal, Account, GroupDetails, and MovieDetail with associated styles | 3
2025-11-26 | Merge: integrated main branch changes into updated-readme branch & Fixed potential memory leak in GetCast.jsx by correcting debounce/subscription handling in component effects | 1
2025-11-27 | Fixed React key prop warning in GroupDetails.jsx by adding stable keys to list items | 1
2025-11-28
2025-11-29
2025-11-30
2025-12-01 | Fixed Navbar CSS to correct Login and Search button scaling and responsive layout | 1
2025-12-02 | Added Railway cloud artifacts (nginx config, .env.railway.example, package updates) and updated server entrypoint for cloud environment | 6
2025-12-03
2025-12-04 | Large deployment updates: synchronized Dockerfiles, package manifests, and docker-compose.yml to create consistent build artifacts for cloud deploys | 4
2025-12-05 | De-bugged cloud deployment issues: updated server/index.js, Docker/Railway configs, and health checks to address deployment failures | 3
2025-12-06 | djusted Railway deploy configs to deploy from repo root; updated railway.json, server Docker/Railway files, and health route for root-deploy behavior | 2
2025-12-07
2025-12-08 | Merged Railway deployment branch into main (integration) | 0.25
2025-12-09
2025-12-10
2025-12-11
2025-12-12 | Backend security hardening: updates to userController, auth helper, rate limiting, validation, routes, and services to improve authentication and request handling | 6
2025-12-13 | Updated documentation files (.env.example, README) with clearer instructions and examples | 1
2025-12-14 | Removed unused passwordValidator service from server as part of a security/cleanup refactor & Merged into main (integration) | 1
2025-12-15 | Implemented favorite-share backend: new favoriteListShareController, favoriteListShareModel, and routes to create and retrieve shared favorite lists and tokens & Merged into main (integration) | 4
2025-12-16 | Added favorite-list sharing UI: ShareModal, useShareApi hook, SharedList page, and account/share-related styles to create and view shareable favorite list links | 5
Added environment/config support for share-link generation (dev vs prod base URL), updated server share controller to read configured base URL
2025-12-17 | Fixed group listing UI and useGroupApi hook issues so group lists display correctly and handle API responses safely | 6
Implemented refresh-token authentication flow and cookie parsing: added cookie-parser usage on server, updated auth helpers, userController/userService, and updated frontend AuthContext, Login, Account, and Navbar to use secure refresh cookies
68
Yhteensä:

## Juho-Pekka Salo
Ryhmä: | 9
Pvm | Tehtävä | Juho-Pekka Salo
2025-11-04 | Käyttöliitymän suunnittelu | 2
2025-11-04 | Tietokannan suunnittelu | 2
2025-11-05 | Versionhallinan käyttöönotto | 2
2025-11-06 | Docker käyttöönotto | 2
2025-11-10 | Backendin aloitus | 3
2025-11-12 | Backendin tekemistä | 3
2025-11-13 | Frontend kuvanhaku ja API yhteys | 3
2025-11-17 | Backend/accountin tekeminen | 3
2025-11-17 | Käyttöliittymän tyylejä | 3
2025-11-18 | Backend/frontend account sivu | 6
2025-11-19 | Account sivun parantelu | 4
2025-11-20 | Delete account/change password | 3
2025-12-25 | Account ja main sivun yhdistämisiä | 4
2025-11-26 | Account sivun asettelu ja muokkaus | 4
2025-12-02 | Bugien korjauksia | 2
2025-12-03 | Bugien korjauksia | 3
2025-12-07 | Sivun julkaisu railwayssa | 4
2025-12-08 | Sivun julkaisu railwayssa | 3
2025-12-08 | Yleisesti käyttöliittymän parantelua ja korjauksia | 4
2025-12-09 | Account sivun lisäyksiä | 4
2025-12-10 | Yleisesti käyttöliittymän parantelua ja korjauksia | 2
2025-12-17 | Yleisesti käyttöliittymän parantelua ja korjauksia | 3
| Yhteensä: | 69

## Konsta Ahvonen
Ryhmä: | 9
2025-11-12 | Oriontoitumista | 4 | Konsta
2023-10-12 | Oriontoitumista | 3.5 | Konsta
2023-10-14 | Oriontoitumsita | 4.5 | Konsta
01/11/2025 Elokuvasivua |  | 1 | Konsta
2025-11-01 | Arvosteluosiota | 3 | Konsta
2025-12-01 | Vastausosiota | 3 | Konsta
2025-12-25 | Navvbaaria | 4 | Konsta
2025-12-01 | Arvostelua | 2 | Konsta
2025-12-01 | Vastausta | 3 | Konsta
2025-12-25 | Tyylittelyä | 2 | Konsta